## Read me
ZX Collabs BIM Outsourcing Procurement Kit
Version 1.0 · reviewed 22 August 2026 · macro-free XLSX
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Purpose | Create one comparable brief, request the same evidence, normalize proposals and preserve a transparent appointment decision for a freelancer, specialist, embedded pod, managed team or internal route.
Five-minute start | 1. Complete Scope Baseline. 2. List required Deliverables. 3. Enter each option in Commercial Normalize and Proposal Comparison. 4. Record evidence and a representative pilot. 5. approve the Decision Record.
Marketplace use | Use the same scope, sample input, output, review period and acceptance test for marketplace proposals and direct procurement. Profile ratings, badges or availability are signals—not project-specific evidence.
Scoring rule | Seven evidence-and-control dimensions are weighted visibly on Lists. A score organizes questions; it does not certify a supplier or predict performance.
Commercial rule | Do not compare fees until scope, review cycles, revisions, change assumptions, software, tax, travel, programme and responsibility are normalized.
Example data | Every organization, person, package, date, score and fee is fictional training data. Replace every sample entry.
Confidentiality | Keep sensitive files in the approved project system. Link controlled evidence; do not embed confidential models, proposals, personal data or credentials in this workbook.
Boundary | Not legal, procurement, tax, security, employment or professional advice; not ISO text or certification; not a substitute for references, contracts, due diligence, technical review or authorized appointments.
ZX transparency | Apply the same evidence, QA, responsibility, security and representative-file questions to ZX Collabs. Public evidence: https://zxcollabs.com/projects/evidence-library/
Discuss a package | Send representative inputs, required outputs, software, programme and review route: https://zxcollabs.com/request-bim-quote/
Direct contact | admin@zxcollabs.com · WhatsApp +91 750 906 7727 · https://www.upwork.com/freelancers/~01041c71222ad5aeb0

## Dashboard
BIM outsourcing procurement dashboard
Live summary from the editable control sheets. Zero is not evidence of completion.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Metric | Current | Decision sequence
Scope decisions confirmed |  | 01 — Establish one scope baseline
Scope decisions open / TBD |  | 02 — Normalize deliverables and commercials
Required deliverables |  | 03 — Review bounded, comparable evidence
Options entered |  | 04 — Run the same representative-file test
Options ready for pilot |  | 05 — Record conditions, authority and residual risk
Evidence missing |  | 06 — Mobilize only after the appointment basis is agreed
Highest evidence score
A higher score does not override missing evidence, security, legal, tax, professional responsibility, availability or contract review.

## Scope Baseline
Comparable BIM outsourcing scope baseline
Record the common appointment basis before any option is priced or scored.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Section | Requirement / decision | Current position | Status | Owner | Due date | Evidence / source | Notes
Project | Project/package name | Northstar Learning Centre — coordination package | Confirmed | Project lead | 2026-08-25
Purpose | Intended model/drawing use | LOD 350 architectural + MEP coordination and coordinated issue set | Confirmed | BIM manager | 2026-08-25
Inputs | Representative source files | Architectural RVT, structural IFC, MEP RVT and sample issue sheet | Confirmed | Information manager | 2026-08-26 | CDE sample package
Outputs | Native files and exchanges | Revit 2026, NWC, IFC4, PDF drawing issue, BCF issue export | Confirmed | BIM manager | 2026-08-26
Standards | Template, naming, coordinates and CDE route | Client template v3; shared coordinates; ISO 19650-aligned project naming | Confirmed | Information manager | 2026-08-27 | BEP section 6 | Not a certification statement
Definition | LOD/LOI or element/use matrix | Element/use matrix controls interfaces; no blanket fabrication reliance | Confirmed | Design manager | 2026-08-27 | Model definition matrix
Programme | Production, review and revision windows | 10-week package; weekly coordination; two client review cycles | Confirmed | Project lead | 2026-08-28
Responsibility | Design authority and approvals | Client design leads retain design approval; supplier authors and coordinates agreed scope | Confirmed | Project lead | 2026-08-28 | Responsibility matrix
Change | Included revisions and change triggers | Two review cycles; revised client input after baseline is assessed before work | Confirmed | Commercial lead | 2026-08-29
Security | Access, storage, subcontracting and deletion | Named accounts; approved CDE only; no subcontracting without approval; closeout deletion confirmation | Confirmed | Security lead | 2026-08-29 | Security questionnaire
Commercial | Currency, tax and validity basis | Compare in USD; tax excluded; proposal validity 30 days | Confirmed | Commercial lead | 2026-08-29
Acceptance | Checks and acceptance authority | Weekly model QA; milestone exchange checklist; acceptance by named client BIM manager | Confirmed | BIM manager | 2026-08-30 | QA plan

## Deliverables
Comparable deliverable schedule
Define purpose, output, quantity, review and acceptance at deliverable level.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Deliverable ID | Title | Discipline | Purpose / use | Native format | Exchange format | Software / version | LOD / LOI basis | Stage / milestone | Quantity / area | First review | Final issue | Included review cycles | Acceptance test | Design authority | Inputs / dependencies | Included? | Notes
DEL-001 | Architectural coordination model | Architecture | Coordination + drawing production | RVT | NWC / IFC4 | Revit 2026 | Element/use matrix | Coordination milestone 01 | Approx. 12,000 sq m | 2026-09-14 | 2026-10-30 | 2 | Coordinates, links, naming, model health and agreed interfaces | Client architect | Client template + structural/MEP models | Yes | Fictional
DEL-002 | Federated issue set | Multidisciplinary | Issue review and closure evidence | NWF / BCF | BCF / PDF | Navisworks Manage 2026 | Issue-based | Weekly | 10 weekly issues | 2026-09-07 | 2026-10-30 | 2 | Exact model versions, issue owner, disposition and verified closure | Client BIM manager | Current discipline exchanges | Yes
DEL-003 | Coordinated plans and sections | Architecture | Client review and coordinated documentation | RVT | PDF / DWG | Revit 2026 | LOD 350 where scoped | Design issue | 28 sheets | 2026-09-21 | 2026-10-30 | 2 | Sheet checklist, revision, references and approval status | Client architect | Accepted coordination decisions | Yes
DEL-004 | Model QA record | All | Exchange readiness evidence | XLSX / PDF | PDF | Project-neutral | Project checks | Each milestone | 3 milestone records | 2026-09-14 | 2026-10-30 | 2 | Named rule, result, owner, corrective action and retest evidence | Client BIM manager | Exact issued model versions | Yes
DEL-005 | Optional walkthrough | Visualization | Stakeholder communication | MP4 | MP4 | To be agreed | Visual only | Final | 1 sequence | 2026-10-16 | 2026-10-30 | 1 | Storyboard, resolution, duration and revision boundary | Client design lead | Approved coordinated model | No | Price separately

## Commercial Normalize
Commercial normalization
Enter amounts exactly as proposed. Exchange rates and comparison currency are user-controlled assumptions.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Option ID | Option label | Route | Currency | Rate to comparison currency | Base fee | Allowance / contingency | Software / licences | Travel / misc. | Taxes / duties amount | Total quoted | Comparable total | Included revisions | Extra revision rate | Included review cycles | Programme weeks | Change / rework basis | Assumptions / exclusions
OPT-A | Fictional Provider A | Defined package | USD | 1 | 48500 | 2500 | 1200 | 0 | 0 |  |  | 2 | 1450 | 2 | 10 | Revised client inputs after baseline use written change route | Excludes site attendance; tax excluded
OPT-B | Fictional Independent Specialist | Independent specialist | USD | 1 | 39200 | 6000 | 2400 | 0 | 0 |  |  | 1 | 120 | 1 | 12 | Hourly for revised inputs and additional cycles | Availability subject to named weekly capacity
OPT-C | Fictional Managed Team | Managed team | USD | 1 | 56500 | 1500 | 0 | 0 | 0 |  |  | 3 | 1800 | 3 | 10 | Change assessed against package baseline | Includes management and independent QA; tax excluded

## Proposal Comparison
Evidence-led proposal comparison
Score only after reviewing relevant evidence. 0 = absent; 5 = strong, comparable and bounded evidence.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Option ID | Option label | Route | Proposal date | Validity date | Availability / start | Relevant evidence 0-5 | Scope comprehension 0-5 | QA + acceptance 0-5 | Information control 0-5 | Responsibility + change 0-5 | Capacity + communication 0-5 | Security + continuity 0-5 | Weighted score /100 | Evidence gaps | Decision gate | Shortlist status | Comparable total | Programme weeks | Notes
OPT-A | Fictional Provider A | Defined package | 2026-08-20 | 2026-09-19 | 2026-09-01 | 4 | 4 | 4 | 4 | 3 | 4 | 3 |  |  |  | Pilot |  |  | Comparable after security/continuity clarification
OPT-B | Fictional Independent Specialist | Independent specialist | 2026-08-21 | 2026-09-20 | 2026-09-08 | 4 | 3 | 3 | 3 | 3 | 4 | 2 |  |  |  | Clarify |  |  | Clarify QA evidence, review capacity and security route
OPT-C | Fictional Managed Team | Managed team | 2026-08-22 | 2026-09-21 | 2026-09-01 | 5 | 4 | 5 | 4 | 4 | 4 | 4 |  |  |  | Pilot |  |  | Highest evidence score; still requires the same representative-file pilot

## Evidence Review
Evidence request + review record
Keep the candidate contribution, relevance and evidence boundary visible.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Evidence ID | Option ID | Decision area | Evidence requested | Evidence received / link | Comparable scope or output? | Contribution boundary stated? | Review result | Reviewer | Review date | Clarification / action | Due date
EVD-001 | OPT-A | Relevant evidence | Redacted LOD 350 coordination deliverable | https://example.invalid/opt-a-evidence | Yes | Yes | Sufficient | Procurement reviewer | 2026-08-23 | Confirm assigned team contribution | 2026-08-27
EVD-002 | OPT-A | Security + continuity | Access, storage, subcontractor and deletion controls | Proposal section 8 | No | Yes | Partial | Security reviewer | 2026-08-23 | Request continuity and deletion evidence | 2026-08-27
EVD-003 | OPT-B | QA + acceptance | QA checklist and closure evidence | Proposal appendix B | Yes | Partial | Partial | BIM manager | 2026-08-23 | Request exact model/version and retest example | 2026-08-27
EVD-004 | OPT-B | Security + continuity | Approved systems and retention route |  | No | No | Missing | Security reviewer | 2026-08-23 | Complete security questionnaire before file access | 2026-08-26
EVD-005 | OPT-C | Relevant evidence | Comparable models, drawings and coordination evidence | https://example.invalid/opt-c-evidence | Yes | Yes | Sufficient | Procurement reviewer | 2026-08-23 | Validate through representative-file pilot | 2026-08-29
EVD-006 | OPT-C | QA + acceptance | Named QA workflow and evidence record | Proposal section 6 | Yes | Yes | Sufficient | BIM manager | 2026-08-23 | Confirm assigned independent reviewer | 2026-08-29
EVD-007 | OPT-C | Responsibility + change | Responsibility matrix and change route | Proposal appendix C | Yes | Yes | Sufficient | Project lead | 2026-08-23 | Align client design authority names | 2026-08-29

## Pilot + Interview
Representative-file pilot + interview record
Give shortlisted routes the same input, timebox, output and acceptance test.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Test ID | Option ID | Type | Question / task | Expected evidence / output | Timebox / due | Reviewer | Result | Score 0-5 | Finding / observation | Action / decision
PIL-001 | OPT-A | Pilot | Review one representative model zone and return setup, clarification and delivery approach | Scope restatement, queries, setup choices, QA route and sample issue output | 2 business days | BIM manager | Partial | 3 | Good scope read; security response incomplete | Clarify before second stage
PIL-002 | OPT-C | Pilot | Review the same representative model zone and return setup, clarification and delivery approach | Same acceptance test as PIL-001 | 2 business days | BIM manager | Pass | 4 | Clear interfaces, QA evidence and decision assumptions | Advance subject to commercials
INT-001 | OPT-A | Interview | Who authors, checks, approves and communicates each output? | Named assigned roles and separation of production from acceptance | 30 minutes | Project lead | Pass | 4 | Roles clear; substitution route pending | Request continuity plan
INT-002 | OPT-B | Interview | How are capacity, working-hour overlap and substitutions controlled? | Named capacity and continuity evidence | 30 minutes | Project lead | Partial | 2 | Single-person dependency not yet mitigated | Clarify availability and backup
INT-003 | OPT-C | Interview | How are design authority, change and additional cycles handled? | Written responsibility and change route | 30 minutes | Commercial lead | Pass | 4 | Route clear subject to appointment wording | Include in award memo
INT-004 | ALL | Control | Which exact files, versions and acceptance tests will be used? | Common issue package and signed test instructions | Before pilot | BIM manager | Pass | 5 | Common basis issued | Retain with procurement record
INT-005 | ALL | Control | What information may be shared before appointment? | Redacted sample and approved access route | Before access | Security reviewer | Pass | 5 | No confidential live project data used | Retain access evidence
INT-006 | ALL | Control | How will conflicts of interest or subcontracting be disclosed? | Written declaration and approval route | Before shortlist | Procurement lead | Pass | 5 | Fictional example declaration recorded | Carry into contract
INT-007 | ALL | Control | How will the selected route be notified and unsuccessful evidence retained/deleted? | Communication, retention and deletion decision | At award | Procurement lead | Not tested | 0 | Complete after decision | Open

## Decision Record
Appointment decision record
Preserve the basis, conditions, authority and next verification gate.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Procurement / package ID | PROC-BIM-001 | Live comparison summary | Value
Project / package | Northstar Learning Centre — coordination package | Options entered
Comparison currency | USD | Ready for pilot
Options reviewed | 3 | Clarification gates
Preferred option | OPT-C — Fictional Managed Team | Missing evidence
Decision date | 2026-08-30 | Open scope decisions
Decision authority | Fictional Project Director | Highest evidence score
Reason for selection | Highest bounded evidence score with visible QA, continuity and change control; subject to the same representative-file pilot and final commercial alignment. | Decision rule | Do not appoint from this score alone
Conditions before appointment | Confirm assigned people, tax position, data-access route, professional responsibility and accepted pilot output.
Commercial basis | USD 58,000 comparable total; 10-week programme; three review cycles; tax excluded.
Key exclusions / residual risks | No site attendance; client retains design approval; changed input after baseline is assessed separately.
Representative-file test | PIL-002 passed with one commercial clarification open.
Security / confidentiality | Approved CDE accounts only; no onward sharing; deletion confirmation at closeout.
Mobilization action | Issue appointment, final scope baseline, responsibility matrix, access list and kickoff agenda.
Unsuccessful options | Notify respectfully; retain only the approved procurement record; delete sensitive submissions per agreed retention.
Approval status | Preferred subject to conditions

## Lists
Controlled lists + scoring weights
Edit project language deliberately. Weights are visible and must total 100%.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Status | Route | Evidence_Result | Shortlist | Pilot_Result | Yes_No | Currency | Scoring dimension | Weight
Confirmed | Defined package | Sufficient | Longlist | Not tested | Yes | USD | Relevant evidence | 15%
Open | Independent specialist | Partial | Clarify | Pass | No | GBP | Scope comprehension | 15%
TBD | Embedded pod | Missing | Shortlisted | Partial |  | EUR | QA + acceptance | 20%
N/A | Managed team | Not applicable | Pilot | Fail |  | AUD | Information + coordination control | 15%
| Internal route |  | Preferred | Not applicable |  | INR | Responsibility + change | 15%
|  |  | Not selected |  |  | AED | Capacity + communication | 10%
[6 empty] | SAR | Security + continuity | 10%
[6 empty] | Other | Total

## Data Dictionary
Data dictionary
Definitions for the workbook’s key inputs and formulas.
FICTIONAL WORKED EXAMPLE — no real provider, client, project, fee or benchmark
Sheet | Field | Definition / control intent | Input or formula
Scope Baseline | Status | Confirmed, Open, TBD or N/A project decision. | Input
Deliverables | Acceptance test | Observable check used by the named acceptance authority. | Input
Commercial Normalize | Comparable total | Total quoted multiplied by a user-entered rate to the comparison currency. | Formula
Proposal Comparison | Weighted score | Seven 0–5 evidence/control scores multiplied by visible weights and scaled to 100. | Formula
Proposal Comparison | Evidence gaps | Seven minus the number of dimensions scored at least 3. Blank scores remain gaps. | Formula
Proposal Comparison | Decision gate | Clarify if any evidence gap remains; otherwise uses evidence-score bands for the next verification step. | Formula
Evidence Review | Contribution boundary | What the candidate actually authored, coordinated, checked or approved. | Input
Pilot + Interview | Representative-file pilot | Same bounded input, timebox, output and acceptance test for shortlisted routes. | Input
Decision Record | Conditions before appointment | Actions that must close before mobilization or file access. | Input
All sheets | Fictional example | Training data only; never a client record, benchmark or provider claim. | Boundary