## Read me
ZX Collabs Coordination & QA Controls
ZX Collabs operational control · Version 1.0 · Reviewed 22 August 2026
Start in five minutes | 1. Edit Lists and project setup. 2. Replace sample rows or begin in the blank tables. 3. Assign named owners and dates. 4. Link evidence rather than embedding confidential files. 5. Review dashboard exceptions in a real meeting.
What this is | A practical, editable starting control for design, BIM and construction delivery teams.
What this is not | Not ISO text or certification, legal or contract advice, safety planning, engineering approval, professional certification, or a substitute for project appointments and authority requirements.
Core rule | A status is only as reliable as its named owner, dated evidence and agreed workflow.
Example data | This edition contains no project records. Use the separate fictional example to see completed rows.
Compatibility | Macro-free XLSX. Designed for Microsoft Excel; should degrade intelligibly in Google Sheets and LibreOffice.
Privacy | The workbook is local and does not upload project data. Control access to the file and linked evidence.
Project tailoring | Adapt terminology, status/suitability codes, approval routes, fields and thresholds to the current project requirements, appointments, CDE and jurisdiction.
Support | Need this mapped to your project, client standard or reporting route? Visit https://zxcollabs.com/request-bim-quote/
License note | Internal and project use is intended. Do not resell, misrepresent as certified, or remove ZX Collabs attribution. Final legal wording requires owner review.

## Lists
Controlled lists
Edit these values to match the project. Codes shown are examples, not universal requirements.
Priority | Issue_Status | Result | Severity | Discipline
Critical | Open | Not run | Critical | Architecture
High | In review | Pass | Major | Structure
Medium | Resolved pending verification | Fail | Moderate | Mechanical
Low | Closed | N/A | Minor | Electrical
| Accepted condition |  |  | Plumbing
| Reopened |  |  | Civil
General

## Check Rules
Coordination check plan
Define tests, discipline pairs, tolerances and ownership before reporting issues.
Rule ID | Rule / Test | Model A | Model B | Discipline Pair | Zone / Level | Tolerance | Frequency | Owner | Decision Authority | Active? | Notes

## Model Versions
Federation model version register
Record the exact files and builds used for each check run.
Model ID | Discipline | Container ID | Revision | Revit / Authoring Build | Export Format | Export Date | Author | Coordinates Checked? | File / Evidence URL | Notes

## Issues
BIM coordination, clash & issue register
Turn test results into owned issues with decisions and closure evidence.
Issue ID | External / BCF ID | Run ID | Raised Date | Discipline Pair | Zone / Level | Issue Class | Priority | Owner | Due Date | Status | Proposed Resolution | Approved Disposition | Affected Container | Verification Run | Evidence URL | Closed Date | Days Open | Overdue? | Reopen Count | Notes

## QA Checks
BIM QA, model health & exchange validation
Record configurable checks, evidence, findings and independent closure.
Check ID | Category | Model / Container | Version / Build | Requirement Source | Method | Threshold / Tolerance | Population / Sample | Checked Count | Failed Count | Severity | Result | Evidence URL | Owner | Target Date | Reviewer | Closure Run | Pass Rate | Overdue? | Notes

## Dashboard
Coordination & QA dashboard
Formula-driven summary. Blank means no records; zero is shown only when a defined population exists.
Metric | Current
Open coordination issues
Overdue issues
Reopened issues
Closed / accepted
Failed QA checks
Overdue QA findings

## Data Dictionary
Data dictionary
Definitions and control intent for the most important fields.
Sheet / table | Field | Definition | Input or formula | Required rule
Check Rules | Tolerance | Project-defined test tolerance; not a universal technical requirement. | Input | Required before run
Issues | Approved Disposition | Decision authorized through the project route. | Input | Required before closure
Issues | Verification Run | Named rerun or review proving closure. | Input | Required for Closed
Issues | Overdue? | Open item with a due date before today. | Formula | Exception flag
QA Checks | Threshold / Tolerance | Configurable acceptance criterion. | Input | Never assume universal limits
QA Checks | Pass Rate | (Checked − failed) / checked population. | Formula | Blank when checked count is zero
QA Checks | N/A | Permitted only with a project reason and reviewer. | Input | Manual approval