## Read me
ZX Collabs Coordination & QA Controls
ZX Collabs operational control · Version 1.0 · Reviewed 22 August 2026
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Start in five minutes | 1. Edit Lists and project setup. 2. Replace sample rows or begin in the blank tables. 3. Assign named owners and dates. 4. Link evidence rather than embedding confidential files. 5. Review dashboard exceptions in a real meeting.
What this is | A practical, editable starting control for design, BIM and construction delivery teams.
What this is not | Not ISO text or certification, legal or contract advice, safety planning, engineering approval, professional certification, or a substitute for project appointments and authority requirements.
Core rule | A status is only as reliable as its named owner, dated evidence and agreed workflow.
Example data | Every organization, person, identifier, date and result is fictional training data. Replace all sample entries.
Compatibility | Macro-free XLSX. Designed for Microsoft Excel; should degrade intelligibly in Google Sheets and LibreOffice.
Privacy | The workbook is local and does not upload project data. Control access to the file and linked evidence.
Project tailoring | Adapt terminology, status/suitability codes, approval routes, fields and thresholds to the current project requirements, appointments, CDE and jurisdiction.
Support | Need this mapped to your project, client standard or reporting route? Visit https://zxcollabs.com/request-bim-quote/
License note | Internal and project use is intended. Do not resell, misrepresent as certified, or remove ZX Collabs attribution. Final legal wording requires owner review.

## Lists
Controlled lists
Edit these values to match the project. Codes shown are examples, not universal requirements.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Priority | Issue_Status | Result | Severity | Discipline
Critical | Open | Not run | Critical | Architecture
High | In review | Pass | Major | Structure
Medium | Resolved pending verification | Fail | Moderate | Mechanical
Low | Closed | N/A | Minor | Electrical
| Accepted condition |  |  | Plumbing
| Reopened |  |  | Civil
General

## Check Rules
Coordination check plan
Define tests, discipline pairs, tolerances and ownership before reporting issues.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Rule ID | Rule / Test | Model A | Model B | Discipline Pair | Zone / Level | Tolerance | Frequency | Owner | Decision Authority | Active? | Notes
CR-001 | Ducts vs structural framing | Mechanical model | Structural model | Mechanical / Structure | All levels | 25 mm project value | Weekly | N. Patel | Design coordination lead | Yes | Tolerance must follow project requirements
CR-002 | Lighting vs ceiling system | Electrical model | Architectural model | Electrical / Architecture | Levels 01-02 | 10 mm project value | Weekly | P. George | Design coordination lead | Yes | Fictional training rule
CR-003 | Door swing vs fixed equipment | Architectural model | Equipment model | Architecture / Equipment | Clinical rooms | 0 mm intersection | Milestone | A. Rao | Design lead | Yes | Review access separately
CR-004 | Pipework vs access zones | Plumbing model | Clearance proxies | Plumbing / Access | Plant rooms | Project-defined | Weekly | N. Patel | FM representative | Yes | Access zone is not a code clearance
CR-005 | Duplicate element scan | Federated model |  | General | All | Exact duplicate | Milestone | M. Lee | BIM manager | Yes | Group duplicates into issues

## Model Versions
Federation model version register
Record the exact files and builds used for each check run.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Model ID | Discipline | Container ID | Revision | Revit / Authoring Build | Export Format | Export Date | Author | Coordinates Checked? | File / Evidence URL | Notes
MV-ARC-024 | Architecture | ARC-ZX-Z1-ZZ-M3-A-0001 | P03 | Revit 2026.2 | RVT/NWC | 2026-08-21 | A. Rao | Yes | https://cde.example/MV-ARC-024 | Fictional
MV-STR-018 | Structure | STR-ZX-Z1-L01-M3-S-2001 | P01 | Revit 2026.1 | RVT/NWC | 2026-08-20 | S. Kumar | Yes | https://cde.example/MV-STR-018 | Fictional
MV-MEP-021 | MEP | MEP-ZX-Z1-ZZ-M3-M-3001 | P01 | Revit 2026.2 | RVT/NWC | 2026-08-22 | N. Patel | Yes | https://cde.example/MV-MEP-021 | Fictional
MV-ELE-011 | Electrical | ELE-ZX-Z1-ZZ-M3-E-3002 | P01 | Revit 2026.2 | RVT/NWC | 2026-08-22 | P. George | Yes | https://cde.example/MV-ELE-011 | Fictional

## Issues
BIM coordination, clash & issue register
Turn test results into owned issues with decisions and closure evidence.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Issue ID | External / BCF ID | Run ID | Raised Date | Discipline Pair | Zone / Level | Issue Class | Priority | Owner | Due Date | Status | Proposed Resolution | Approved Disposition | Affected Container | Verification Run | Evidence URL | Closed Date | Days Open | Overdue? | Reopen Count | Notes
ISS-001 | BCF-1001 | RUN-2026-08-22 | 2026-08-22 | Mechanical / Structure | Level 01 | Hard clash | High | N. Patel | 2026-08-27 | Resolved pending verification | Reroute duct below beam | Approved by coordination lead | MEP-ZX-Z1-ZZ-M3-M-3001 |  | https://cde.example/ISS-001
ISS-002 | BCF-1002 | RUN-2026-08-22 | 2026-08-22 | Electrical / Architecture | Level 02 | Clearance | Medium | P. George | 2026-08-29 | Open | Shift luminaire within ceiling module |  | ELE-ZX-Z1-ZZ-M3-E-3002 |  | https://cde.example/ISS-002
ISS-003 | BCF-1003 | RUN-2026-08-15 | 2026-08-15 | Plumbing / Structure | Level 01 | Hard clash | Critical | N. Patel | 2026-08-18 | Reopened | Revise sleeve request | Awaiting structural decision | MEP-ZX-Z1-ZZ-M3-M-3001 |  | https://cde.example/ISS-003
ISS-004 | BCF-0992 | RUN-2026-08-15 | 2026-08-15 | Architecture / Equipment | Level 01 | Access | High | A. Rao | 2026-08-20 | Closed | Move equipment 150 mm | Approved by design lead | ARC-ZX-Z1-ZZ-M3-A-0001 | RUN-2026-08-22 | https://cde.example/ISS-004 | 2026-08-22
ISS-005 | BCF-0993 | RUN-2026-08-15 | 2026-08-15 | Mechanical / Architecture | Plant room | Clearance | Medium | N. Patel | 2026-08-24 | Accepted condition | Record agreed maintenance route | Accepted by FM representative | MEP-ZX-Z1-ZZ-M3-M-3001 | RUN-2026-08-22 | https://cde.example/ISS-005 | 2026-08-22
ISS-006 | BCF-1005 | RUN-2026-08-22 | 2026-08-22 | General | All | Duplicate | Low | M. Lee | 2026-08-26 | Open | Remove duplicate instances |  | ARC-ZX-Z1-ZZ-M3-A-0001 |  | https://cde.example/ISS-006
ISS-007 | BCF-1008 | RUN-2026-08-22 | 2026-08-22 | Architecture / Structure | Level 02 | Interface | High | A. Rao | 2026-08-30 | In review | Confirm opening set-out | Option issued for review | ARC-ZX-Z1-ZZ-M3-A-0001 |  | https://cde.example/ISS-007
Formulas:
Days Open = IF([Issue ID]="","",IF([Closed Date]="",TODAY()-[Raised Date],[Closed Date]-[Raised Date]))
Overdue? = IF([Issue ID]="","",IF(AND([Status]<>"Closed",[Status]<>"Accepted condition",[Due Date]<TODAY()),"Overdue",""))

## QA Checks
BIM QA, model health & exchange validation
Record configurable checks, evidence, findings and independent closure.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Check ID | Category | Model / Container | Version / Build | Requirement Source | Method | Threshold / Tolerance | Population / Sample | Checked Count | Failed Count | Severity | Result | Evidence URL | Owner | Target Date | Reviewer | Closure Run | Pass Rate | Overdue? | Notes
QA-001 | Coordinates / units | MV-ARC-024 | Revit 2026.2 | BEP 6.3 | Manual + coordinate report | Project coordinate control | Full model | 1 | 0 | Critical | Pass | https://cde.example/QA-001 | M. Lee | 2026-08-22 | D. Shah | RUN-2026-08-22
QA-002 | Warnings | MV-ARC-024 | Revit 2026.2 | Project QA plan | Automated report | Configurable by warning type | Full model | 142 | 7 | Major | Fail | https://cde.example/QA-002 | A. Rao | 2026-08-25 | M. Lee
QA-003 | Sheets / revisions | ARC-ZX-Z1-L01-DR-A-1001 | P02 | Issue checklist | Manual sample | All issued sheets | 12 sheets | 12 | 0 | Major | Pass | https://cde.example/QA-003 | A. Rao | 2026-08-24 | M. Lee | ISSUE-P02
QA-004 | Required parameters | MV-MEP-021 | Revit 2026.2 | EIR 4.4 | Scheduled audit | Required fields only | 480 elements | 480 | 22 | Major | Fail | https://cde.example/QA-004 | N. Patel | 2026-08-28 | M. Lee
QA-005 | IFC schema | IFC-EXPORT-007 | IFC 4.3 | Exchange requirement | buildingSMART validator | Schema validity | 1 file | 1 | 0 | Critical | Pass | https://validate.buildingsmart.org/ | M. Lee | 2026-08-22 | D. Shah | IFC-RUN-007
QA-006 | IFC properties | IFC-EXPORT-007 | IFC 4.3 | IDS-001 | IDS checker | Required property set | 120 objects | 120 | 9 | Major | Fail | https://cde.example/QA-006 | M. Lee | 2026-08-27 | D. Shah
QA-007 | Family performance | MV-ARC-024 | Revit 2026.2 | Content standard | Inventory audit | Project-defined size / complexity | 68 families | 68 | 2 | Moderate | Fail | https://cde.example/QA-007 | A. Rao | 2026-08-30 | M. Lee
Formulas:
Overdue? = IF([Check ID]="","",IF(AND([Result]<>"Pass",[Result]<>"N/A",[Target Date]<TODAY()),"Overdue",""))

## Dashboard
Coordination & QA dashboard
Formula-driven summary. Blank means no records; zero is shown only when a defined population exists.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Metric | Current
Open coordination issues
Overdue issues
Reopened issues
Closed / accepted
Failed QA checks
Overdue QA findings

## Data Dictionary
Data dictionary
Definitions and control intent for the most important fields.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Sheet / table | Field | Definition | Input or formula | Required rule
Check Rules | Tolerance | Project-defined test tolerance; not a universal technical requirement. | Input | Required before run
Issues | Approved Disposition | Decision authorized through the project route. | Input | Required before closure
Issues | Verification Run | Named rerun or review proving closure. | Input | Required for Closed
Issues | Overdue? | Open item with a due date before today. | Formula | Exception flag
QA Checks | Threshold / Tolerance | Configurable acceptance criterion. | Input | Never assume universal limits
QA Checks | Pass Rate | (Checked − failed) / checked population. | Formula | Blank when checked count is zero
QA Checks | N/A | Permitted only with a project reason and reviewer. | Input | Manual approval