## Read me
ZX Collabs Design & Construction Decision Controls
ZX Collabs operational control · Version 1.0 · Reviewed 22 August 2026
Start in five minutes | 1. Edit Lists and project setup. 2. Replace sample rows or begin in the blank tables. 3. Assign named owners and dates. 4. Link evidence rather than embedding confidential files. 5. Review dashboard exceptions in a real meeting.
What this is | A practical, editable starting control for design, BIM and construction delivery teams.
What this is not | Not ISO text or certification, legal or contract advice, safety planning, engineering approval, professional certification, or a substitute for project appointments and authority requirements.
Core rule | A status is only as reliable as its named owner, dated evidence and agreed workflow.
Example data | This edition contains no project records. Use the separate fictional example to see completed rows.
Compatibility | Macro-free XLSX. Designed for Microsoft Excel; should degrade intelligibly in Google Sheets and LibreOffice.
Privacy | The workbook is local and does not upload project data. Control access to the file and linked evidence.
Project tailoring | Adapt terminology, status/suitability codes, approval routes, fields and thresholds to the current project requirements, appointments, CDE and jurisdiction.
Support | Need this mapped to your project, client standard or reporting route? Visit https://zxcollabs.com/request-bim-quote/
License note | Internal and project use is intended. Do not resell, misrepresent as certified, or remove ZX Collabs attribution. Final legal wording requires owner review.

## Lists
Controlled lists
Edit these values to match the project. Codes shown are examples, not universal requirements.
Priority | RFI_Status | Submittal_Status | Decision_Status | Change_Status
Critical | Draft | Planned | Required | Proposed
High | Open | Submitted | Options in review | Under review
Medium | Answered | In review | Approved | Approved
Low | Incorporation pending | Revise and resubmit | Rejected | Rejected
| Closed | Accepted | Superseded | Implemented
| Cancelled | Rejected |  | Verified
Superseded

## RFI-TQ
RFI & technical query register
Separate questions, responses, incorporation and verification so “answered” does not automatically mean “closed.”
RFI / TQ ID | Raised Date | Raised By | Discipline | Zone | Question | Reason / Impact | Drawing / Model / Spec Refs | Responder | Response Due | Ball in Court | Priority | Status | Response Date | Accepted Answer | Linked Decision | Linked Change | Incorporated Container / Revision | Verified By | Verified Date | Age Days | SLA Breach? | Notes

## Submittals
Submittal & sample register
Track review cycles, procurement float and final acceptance without treating a response code as automatic approval.
Submittal ID | Package / Spec Section | Supplier | Required on Site | Lead Time Days | Planned Submit | Actual Submit | Review Due | Response Code | Cycle | Status | Forecast Acceptance | Final Acceptance | Procurement Float Days | Owner | Evidence URL | Notes

## Decisions
Design & project decision log
Record options, authority, required dates and affected information so decisions remain traceable.
Decision ID | Raised Date | Decision Required | Options | Recommendation | Decision Authority | Required By | Status | Decision | Decision Date | Assumptions | Affected Deliverables | Supersedes | Evidence URL | Notes

## Changes
Linked change control
Keep proposed, approved, implemented and verified impacts distinct.
Change ID | Origin / Link | Raised Date | Description | Reason | Affected Scope / Containers | Proposed Cost Impact | Proposed Time Days | Status | Decision Authority | Decision Date | Approved Cost Impact | Approved Time Days | Implementation Owner | Implemented Date | Verification Evidence | Verified Date | Notes

## Dashboard
Design & construction decisions dashboard
Formula-driven summary. Blank means no records; zero is shown only when a defined population exists.
Metric | Current
Open RFIs / TQs
RFI SLA breaches
Submittals in review
Submittals needing resubmission
Decisions required / in review
Approved changes awaiting verification

## Data Dictionary
Data dictionary
Definitions and control intent for the most important fields.
Sheet / table | Field | Definition | Input or formula | Required rule
RFI-TQ | Status | Answered is distinct from incorporated and verified Closed. | Input | Follow project response route
RFI-TQ | SLA Breach? | Open record whose response due date is before today. | Formula | Exception flag
Submittals | Procurement Float | Required-on-site minus forecast/final acceptance and lead time. | Formula | Negative means potential risk
Submittals | Response Code | Project-defined review response; never automatic approval. | Input | Map to project procedure
Decisions | Decision Authority | Named role authorized to decide. | Input | Required for approval
Changes | Approved impacts | Kept separate from proposed impacts. | Input | Only after authorized decision
Changes | Verified | Implementation checked against dated evidence. | Input | Required to close