## Read me
ZX Collabs Design & Construction Decision Controls
ZX Collabs operational control · Version 1.0 · Reviewed 22 August 2026
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Start in five minutes | 1. Edit Lists and project setup. 2. Replace sample rows or begin in the blank tables. 3. Assign named owners and dates. 4. Link evidence rather than embedding confidential files. 5. Review dashboard exceptions in a real meeting.
What this is | A practical, editable starting control for design, BIM and construction delivery teams.
What this is not | Not ISO text or certification, legal or contract advice, safety planning, engineering approval, professional certification, or a substitute for project appointments and authority requirements.
Core rule | A status is only as reliable as its named owner, dated evidence and agreed workflow.
Example data | Every organization, person, identifier, date and result is fictional training data. Replace all sample entries.
Compatibility | Macro-free XLSX. Designed for Microsoft Excel; should degrade intelligibly in Google Sheets and LibreOffice.
Privacy | The workbook is local and does not upload project data. Control access to the file and linked evidence.
Project tailoring | Adapt terminology, status/suitability codes, approval routes, fields and thresholds to the current project requirements, appointments, CDE and jurisdiction.
Support | Need this mapped to your project, client standard or reporting route? Visit https://zxcollabs.com/request-bim-quote/
License note | Internal and project use is intended. Do not resell, misrepresent as certified, or remove ZX Collabs attribution. Final legal wording requires owner review.

## Lists
Controlled lists
Edit these values to match the project. Codes shown are examples, not universal requirements.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Priority | RFI_Status | Submittal_Status | Decision_Status | Change_Status
Critical | Draft | Planned | Required | Proposed
High | Open | Submitted | Options in review | Under review
Medium | Answered | In review | Approved | Approved
Low | Incorporation pending | Revise and resubmit | Rejected | Rejected
| Closed | Accepted | Superseded | Implemented
| Cancelled | Rejected |  | Verified
Superseded

## RFI-TQ
RFI & technical query register
Separate questions, responses, incorporation and verification so “answered” does not automatically mean “closed.”
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
RFI / TQ ID | Raised Date | Raised By | Discipline | Zone | Question | Reason / Impact | Drawing / Model / Spec Refs | Responder | Response Due | Ball in Court | Priority | Status | Response Date | Accepted Answer | Linked Decision | Linked Change | Incorporated Container / Revision | Verified By | Verified Date | Age Days | SLA Breach? | Notes
RFI-001 | 2026-08-10 | Site team | Architecture | Level 01 | Confirm door-head condition at corridor junction | Detail conflicts with reflected ceiling zone | ARC-1001 / Detail 4 | Design lead | 2026-08-15 | Design lead | High | Closed | 2026-08-14 | Use revised detail option B | DEC-003 | CHG-002 | ARC-1001 P02 | M. Lee | 2026-08-20
RFI-002 | 2026-08-16 | MEP coordinator | Mechanical | Plant room | Confirm maintenance clearance route | Current arrangement restricts service access | MEP-M3-3001 / Spec 23 | FM representative | 2026-08-22 | FM representative | High | Answered | 2026-08-21 | Retain route shown in markup | DEC-004
RFI-003 | 2026-08-18 | Structural coordinator | Structure | Level 01 | Confirm sleeve dimensions and set-out | Pipe route crosses transfer beam | STR-M3-2001 / MEP-M3-3001 | Design lead | 2026-08-21 | Design lead | Critical | Open
TQ-004 | 2026-08-20 | Architect | Architecture | Level 02 | Clarify finish transition at doorway | Schedule and detail use different finish codes | ARC-SH-5002 / Detail 8 | Interior designer | 2026-08-27 | Interior designer | Medium | Open
RFI-005 | 2026-08-21 | Electrical coordinator | Electrical | Level 02 | Confirm revised lighting control zones | Owner comment affects circuit grouping | ELE-4101 / Owner comment 17 | Electrical designer | 2026-08-29 | Electrical designer | Medium | Incorporation pending | 2026-08-22 | Use four control zones | DEC-006 | CHG-004 | ELE-4101 P02
RFI-006 | 2026-08-22 | Contractor | General | Ground floor | Confirm issue priority for entrance package | Programme requires release sequence | Package schedule | Project manager | 2026-08-25 | Project manager | High | Draft
Formulas:
Age Days = IF([RFI / TQ ID]="","",IF([Verified Date]="",TODAY()-[Raised Date],[Verified Date]-[Raised Date]))
SLA Breach? = IF([RFI / TQ ID]="","",IF(AND([Status]<>"Closed",[Response Due]<TODAY()),"Breach",""))

## Submittals
Submittal & sample register
Track review cycles, procurement float and final acceptance without treating a response code as automatic approval.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Submittal ID | Package / Spec Section | Supplier | Required on Site | Lead Time Days | Planned Submit | Actual Submit | Review Due | Response Code | Cycle | Status | Forecast Acceptance | Final Acceptance | Procurement Float Days | Owner | Evidence URL | Notes
SUB-001 | Doors / 08 10 00 | Fictional Doors Ltd | 2026-10-15 | 35 | 2026-08-10 | 2026-08-11 | 2026-08-20 | Revise | 1 | Revise and resubmit | 2026-08-30
SUB-002 | Ceilings / 09 50 00 | Northstar Interiors | 2026-10-01 | 28 | 2026-08-12 | 2026-08-12 | 2026-08-21 | Accepted | 1 | Accepted | 2026-08-21 | 2026-08-21
SUB-003 | Lighting / 26 50 00 | Sample Lighting Co | 2026-11-10 | 42 | 2026-08-22 |  | 2026-09-02 |  | 1 | Planned | 2026-09-02
SUB-004 | Floor finishes / 09 60 00 | Northstar Finishes | 2026-10-20 | 30 | 2026-08-18 | 2026-08-19 | 2026-08-28 | In review | 1 | In review | 2026-08-28
SUB-005 | Mechanical equipment / 23 70 00 | Fictional Mechanical | 2026-12-01 | 70 | 2026-08-15 | 2026-08-16 | 2026-08-25 | Accepted with comments | 1 | Accepted | 2026-08-25 | 2026-08-25

## Decisions
Design & project decision log
Record options, authority, required dates and affected information so decisions remain traceable.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Decision ID | Raised Date | Decision Required | Options | Recommendation | Decision Authority | Required By | Status | Decision | Decision Date | Assumptions | Affected Deliverables | Supersedes | Evidence URL | Notes
DEC-003 | 2026-08-10 | Door-head condition at corridor junction | A: retain detail / B: revised trim | Option B | Design lead | 2026-08-15 | Approved | Use revised detail option B | 2026-08-14 | Subject to ceiling coordination | ARC-1001 |  | https://cde.example/DEC-003
DEC-004 | 2026-08-16 | Maintenance route in plant room | A: shift equipment / B: retain marked route | Retain marked route | FM representative | 2026-08-22 | Approved | Retain route shown in markup | 2026-08-21 | Access zone remains clear | MEP-M3-3001 |  | https://cde.example/DEC-004
DEC-005 | 2026-08-18 | Sleeve set-out at transfer beam | A: reroute / B: structural opening review | Review both | Design lead | 2026-08-21 | Options in review |  |  | No installation until approved | STR-M3-2001 / MEP-M3-3001
DEC-006 | 2026-08-20 | Lighting control zoning | A: two zones / B: four zones | Four zones | Owner representative | 2026-08-24 | Approved | Use four control zones | 2026-08-22 | Budget impact through CHG-004 | ELE-4101 |  | https://cde.example/DEC-006
DEC-007 | 2026-08-22 | Entrance package issue sequence | A: full package / B: early entrance subset | Early subset | Project manager | 2026-08-25 | Required |  |  | Requires drawing list confirmation | ARC entrance package

## Changes
Linked change control
Keep proposed, approved, implemented and verified impacts distinct.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Change ID | Origin / Link | Raised Date | Description | Reason | Affected Scope / Containers | Proposed Cost Impact | Proposed Time Days | Status | Decision Authority | Decision Date | Approved Cost Impact | Approved Time Days | Implementation Owner | Implemented Date | Verification Evidence | Verified Date | Notes
CHG-002 | RFI-001 | 2026-08-14 | Revise door-head detail | Resolve ceiling junction conflict | ARC-1001 |  | 1 | Verified | Project manager | 2026-08-15 |  | 1 | A. Rao | 2026-08-19 | https://cde.example/CHG-002 | 2026-08-20 | Fictional no-cost sample
CHG-003 | RFI-003 | 2026-08-18 | Potential sleeve / route change | Transfer beam interface | STR-M3-2001 / MEP-M3-3001 |  |  | Under review | Design lead |  |  |  | N. Patel |  |  |  | Do not assume approval
CHG-004 | RFI-005 | 2026-08-22 | Revise lighting control zones | Owner decision DEC-006 | ELE-4101 | 2500 | 2 | Approved | Project manager | 2026-08-22 | 1800 | 1 | P. George |  |  |  | Fictional currency-neutral values
CHG-005 | DEC-007 | 2026-08-22 | Early entrance package issue | Programme sequencing | ARC entrance package |  | -2 | Proposed | Project manager |  |  |  | A. Rao |  |  |  | Time saving is unapproved

## Dashboard
Design & construction decisions dashboard
Formula-driven summary. Blank means no records; zero is shown only when a defined population exists.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Metric | Current
Open RFIs / TQs
RFI SLA breaches
Submittals in review
Submittals needing resubmission
Decisions required / in review
Approved changes awaiting verification

## Data Dictionary
Data dictionary
Definitions and control intent for the most important fields.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Sheet / table | Field | Definition | Input or formula | Required rule
RFI-TQ | Status | Answered is distinct from incorporated and verified Closed. | Input | Follow project response route
RFI-TQ | SLA Breach? | Open record whose response due date is before today. | Formula | Exception flag
Submittals | Procurement Float | Required-on-site minus forecast/final acceptance and lead time. | Formula | Negative means potential risk
Submittals | Response Code | Project-defined review response; never automatic approval. | Input | Map to project procedure
Decisions | Decision Authority | Named role authorized to decide. | Input | Required for approval
Changes | Approved impacts | Kept separate from proposed impacts. | Input | Only after authorized decision
Changes | Verified | Implementation checked against dated evidence. | Input | Required to close