## Read me
ZX Collabs Information Delivery Controls
ZX Collabs operational control · Version 1.0 · Reviewed 22 August 2026
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Start in five minutes | 1. Edit Lists and project setup. 2. Replace sample rows or begin in the blank tables. 3. Assign named owners and dates. 4. Link evidence rather than embedding confidential files. 5. Review dashboard exceptions in a real meeting.
What this is | A practical, editable starting control for design, BIM and construction delivery teams.
What this is not | Not ISO text or certification, legal or contract advice, safety planning, engineering approval, professional certification, or a substitute for project appointments and authority requirements.
Core rule | A status is only as reliable as its named owner, dated evidence and agreed workflow.
Example data | Every organization, person, identifier, date and result is fictional training data. Replace all sample entries.
Compatibility | Macro-free XLSX. Designed for Microsoft Excel; should degrade intelligibly in Google Sheets and LibreOffice.
Privacy | The workbook is local and does not upload project data. Control access to the file and linked evidence.
Project tailoring | Adapt terminology, status/suitability codes, approval routes, fields and thresholds to the current project requirements, appointments, CDE and jurisdiction.
Support | Need this mapped to your project, client standard or reporting route? Visit https://zxcollabs.com/request-bim-quote/
License note | Internal and project use is intended. Do not resell, misrepresent as certified, or remove ZX Collabs attribution. Final legal wording requires owner review.

## Lists
Controlled lists
Edit these values to match the project. Codes shown are examples, not universal requirements.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Discipline | CDE_State | Suitability | Status | Priority
Architecture | Work in Progress | Project-defined review | Not started | Critical
Structure | Shared | For coordination | In progress | High
Mechanical | Published | For information | Ready for review | Medium
Electrical | Archived | For construction | Issued | Low
Plumbing |  | As-built / record | Accepted
Civil |  | Not applicable | Rejected
Landscape |  |  | Blocked
General

## Deliverables
Drawing, model & information container register
Plan, issue and trace drawings, models and other controlled information containers.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Container ID | Title | Type | Discipline | Package | Responsible | Planned Shared | Planned Published | Forecast Published | Actual Issue | Revision | CDE State | Suitability | Purpose of Issue | Checker | Approver | Transmittal | CDE URL | Days to Due | Variance Days | RAG | Metadata % | Notes
ARC-ZX-Z1-L01-DR-A-1001 | Ground floor general arrangement | Drawing | Architecture | GA package | A. Rao | 2026-08-18 | 2026-08-25 | 2026-08-25 | 2026-08-24 | P02 | Published | For coordination | Coordination | M. Lee | D. Shah | TR-014 | https://cde.example/ARC-1001
STR-ZX-Z1-L01-M3-S-2001 | Level 01 structural model | Model | Structure | Coordination | S. Kumar | 2026-08-20 | 2026-08-29 | 2026-09-02 |  | P01 | Shared | For coordination | Coordination | J. Smith | K. Chen
MEP-ZX-Z1-ZZ-M3-M-3001 | Federated MEP model | Model | Mechanical | Coordination | N. Patel | 2026-08-19 | 2026-08-26 | 2026-08-31 |  | P01 | Shared | For coordination | Coordination | M. Lee | K. Chen
ARC-ZX-Z1-L02-DR-A-1101 | Level 02 reflected ceiling plan | Drawing | Architecture | RCP package | A. Rao | 2026-08-24 | 2026-09-03 | 2026-09-03 |  | P01 | Work in Progress | Project-defined review | Review | M. Lee | D. Shah
ELE-ZX-Z1-ZZ-DR-E-4101 | Lighting layout | Drawing | Electrical | MEP issue | P. George | 2026-08-22 | 2026-08-28 | 2026-08-28 |  | P01 | Shared | For coordination | Coordination | N. Patel | K. Chen
ARC-ZX-Z1-ZZ-SH-A-5001 | Door schedule | Schedule | Architecture | Schedules | A. Rao | 2026-08-20 | 2026-08-27 | 2026-08-27 |  | P01 | Ready for review | Project-defined review | Review | M. Lee | D. Shah
GEN-ZX-Z1-ZZ-RP-Z-9001 | Weekly BIM coordination report | Report | General | Management | M. Lee | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-22 | P01 | Published | For information | Information | M. Lee | D. Shah | TR-015 | https://cde.example/RP-9001
ARC-ZX-Z1-ZZ-M3-A-0001 | Architectural authoring model | Model | Architecture | Coordination | A. Rao | 2026-08-23 | 2026-09-05 | 2026-09-05 |  | P03 | Work in Progress | For coordination | Coordination | M. Lee | D. Shah
Formulas:
Days to Due = IF([Container ID]="","",IF([Actual Issue]<>"",0,[Planned Published]-TODAY()))
Variance Days = IF([Container ID]="","",IF([Actual Issue]="",TODAY()-[Planned Published],[Actual Issue]-[Planned Published]))

## MIDP-TIDP
MIDP / TIDP information delivery planner
Plan task-team deliverables, dependencies, milestones, reviews and acceptance.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Task ID | Parent MIDP | Information Deliverable | Task Team | Owner / Author | Checker | Approver | Purpose | Requirement Ref | Format | Predecessor | Milestone | Planned Start | Planned Share | Planned Publish | Forecast Publish | Actual Publish | CDE State | Acceptance | Days to Publish | Blocked? | Notes
TIDP-ARC-001 | MIDP-001 | Ground floor GA drawing | Architecture | A. Rao | M. Lee | D. Shah | Coordination | EIR-4.2 | PDF/RVT |  | Design coordination 02 | 2026-08-10 | 2026-08-18 | 2026-08-25 | 2026-08-25 | 2026-08-24 | Published | Accepted
TIDP-STR-001 | MIDP-001 | Level 01 structural model | Structure | S. Kumar | J. Smith | K. Chen | Coordination | EIR-4.2 | RVT/IFC | TIDP-ARC-001 | Design coordination 02 | 2026-08-12 | 2026-08-20 | 2026-08-29 | 2026-09-02 |  | Shared | In review
TIDP-MEP-001 | MIDP-001 | Federated MEP model | MEP | N. Patel | M. Lee | K. Chen | Coordination | EIR-4.2 | RVT/NWC | TIDP-STR-001 | Design coordination 02 | 2026-08-13 | 2026-08-19 | 2026-08-26 | 2026-08-31 |  | Shared | In review
TIDP-ARC-002 | MIDP-002 | Level 02 RCP drawing | Architecture | A. Rao | M. Lee | D. Shah | Review | PIR-2.1 | PDF/DWG | TIDP-MEP-001 | Design review 03 | 2026-08-22 | 2026-08-24 | 2026-09-03 | 2026-09-03 |  | Work in Progress | Not submitted
TIDP-ELE-001 | MIDP-002 | Lighting layout | Electrical | P. George | N. Patel | K. Chen | Coordination | PIR-2.1 | PDF/RVT | TIDP-ARC-002 | Design review 03 | 2026-08-18 | 2026-08-22 | 2026-08-28 | 2026-08-28 |  | Shared | Not submitted
TIDP-GEN-001 | MIDP-000 | Weekly BIM report | BIM management | M. Lee | M. Lee | D. Shah | Information | BEP-9 | PDF | TIDP-ARC-001 | Weekly report | 2026-08-18 | 2026-08-21 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Published | Accepted
Formulas:
Days to Publish = IF([Task ID]="","",IF([Actual Publish]<>"",0,[Planned Publish]-TODAY()))

## Transmittals
Transmittal register
Record exactly what was issued, to whom, when and through which controlled route.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Transmittal ID | Issue Date | Sender | Recipient | Purpose | Container IDs / Package | Revision Basis | Delivery Method | Acknowledged Date | Status | CDE / Evidence URL | Notes
TR-014 | 2026-08-24 | M. Lee | Design coordination team | Coordination | ARC-ZX-Z1-L01-DR-A-1001 | P02 | CDE transmittal | 2026-08-24 | Acknowledged | https://cde.example/TR-014 | Fictional example
TR-015 | 2026-08-22 | M. Lee | Project leadership | Information | GEN-ZX-Z1-ZZ-RP-Z-9001 | P01 | CDE transmittal | 2026-08-22 | Acknowledged | https://cde.example/TR-015 | Fictional example
TR-016 | 2026-08-22 | N. Patel | Coordination team | Coordination | MEP-ZX-Z1-ZZ-M3-M-3001 | P01 | CDE transmittal |  | Issued | https://cde.example/TR-016 | Awaiting acknowledgement

## Dashboard
Information delivery dashboard
Formula-driven summary. Blank means no records; zero is shown only when a defined population exists.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Metric | Current
Planned deliverables
Published / archived
Overdue / red
Due within 7 days
Accepted TIDP items
Blocked dependencies

## Data Dictionary
Data dictionary
Definitions and control intent for the most important fields.
FICTIONAL TRAINING EXAMPLE — replace every sample entry before project use
Sheet / table | Field | Definition | Input or formula | Required rule
Deliverables | Container ID | Project-controlled identifier stored as text. | Input | Required for every record
Deliverables | CDE State | Work in Progress, Shared, Published or Archived workflow state. | Input | Use project-defined route
Deliverables | Suitability | Project-defined suitability or status; not a universal code. | Input | Required before issue
Deliverables | RAG | Complete when published/archived; otherwise red if overdue, amber if due within seven days. | Formula | Planning alert only
MIDP-TIDP | Acceptance | Distinct from publishing. Records the appointed review outcome. | Input | Manual and attributable
MIDP-TIDP | Blocked? | Flags a missing or unaccepted named predecessor. | Formula | Dependency control
Transmittals | Acknowledged Date | Date the recipient or system confirmed controlled receipt. | Input | Required to prove acknowledgement