## Read me
ZX Collabs Revit Family QA & Release Kit
Version 1.0 · Reviewed 22 August 2026 · Macro-free XLSX
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Start here | 1. Register every candidate family. 2. Audit parameters and types. 3. Flex dimensions, formulas, visibility and hosting. 4. Record performance tests. 5. Complete release checks. 6. Release only from verified evidence.
Purpose | A structured audit and release-control workbook for Revit families. It can support internal libraries, project content and supplier submissions.
Not included | This workbook does not contain, generate or certify native Revit family files. Example rows are fictional and do not represent tested ZX content.
Minimum evidence | Revit version/build, family file fingerprint or controlled location, tested types, reviewer, dated results, issue ownership and final release approval.
Test rule | Open and test in every supported Revit version. Flex boundary values and realistic combinations—not only default dimensions.
Performance rule | Measure representative load/regeneration behavior inside a controlled test project. File size alone does not prove efficiency.
Safety boundary | Family geometry, connectors, clearances, accessibility zones and classification are not engineering, code, life-safety or manufacturer approval.
License boundary | Confirm that the source, license and redistribution terms permit the intended use. Do not repackage third-party content without permission.
Example edition | All names, metrics, people, dates and results are fictional training data. Replace them before use.
Compatibility | Designed for Microsoft Excel. Expected to degrade intelligibly in Google Sheets and LibreOffice.
Project support | For family strategy, custom content or library QA, visit https://zxcollabs.com/request-bim-quote/

## Lists
Controlled lists
Adapt these values to the content standard and supported Revit environment.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Category | Host | Status | Result | Risk | Yes_No | Parameter_Class | Parameter_Mode | Release_Status
Generic Models | Unhosted | Candidate | Not tested | Low | Yes | Family | Type | Hold
Detail Items | Face based | In audit | Pass | Moderate | No | Shared | Instance | Conditional release
Specialty Equipment | Wall based | Corrections required | Pass with note | High | N/A | Built-in |  | Released
Mechanical Equipment | Ceiling based | Ready for approval | Fail | Critical |  |  |  | Rejected
Electrical Fixtures | Floor based | Released | N/A |  |  |  |  | Retired
Plumbing Fixtures | Roof based | Retired
Furniture | Work plane based | Rejected
Doors | Line based
Windows
Other

## Family Inventory
Family inventory & provenance
Identify every file, source, supported version, use and review status before detailed QA.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Family ID | File Name | Category | Host Type | Revit Version | Source / Publisher | License Checked? | Author / Custodian | Review Date | Status | File Size KB | Type Count | Nested Family Count | Connector Count | Shared Parameters? | Classification | Intended Use | Project Risk | Controlled File / Evidence URL | Notes | Record Complete %
FAM-001 | ZX_Clearance_Box_Generic.rfa | Generic Models | Unhosted | 2022 | ZX Collabs fictional sample | Yes | A. Tester | 2026-08-20 | Corrections required | 420 | 4 | 0 | 0 | Yes | Project-defined | Coordination clearance planning | Moderate | https://cde.example/FAM-001 | Fictional only
FAM-002 | ZX_Opening_Reservation_Rectangular.rfa | Generic Models | Face based | 2022 | ZX Collabs fictional sample | Yes | A. Tester | 2026-08-21 | Ready for approval | 510 | 6 | 0 | 0 | Yes | Project-defined | Opening reservation coordination | High | https://cde.example/FAM-002 | Fictional only
FAM-003 | ZX_Equipment_Envelope_Generic.rfa | Specialty Equipment | Unhosted | 2022 | ZX Collabs fictional sample | Yes | B. Reviewer | 2026-08-21 | In audit | 680 | 3 | 0 | 0 | No | Project-defined | Early equipment envelope | Moderate | https://cde.example/FAM-003 | Fictional only
FAM-004 | ZX_Detail_Direction_Arrow.rfa | Detail Items | Line based | 2022 | ZX Collabs fictional sample | Yes | B. Reviewer | 2026-08-22 | Released | 96 | 2 | 0 | 0 | No | Project-defined | 2D drafting annotation | Low | https://cde.example/FAM-004 | Fictional only
FAM-005 | ThirdParty_Sample.rfa | Furniture | Unhosted | 2021 | Unverified fictional source | No |  |  | Hold | 2450 | 18 | 4 | 0 | Unknown |  | Evaluation only | High |  | Do not redistribute

## Parameter Audit
Parameter schema audit
Test naming, data type, GUID, type/instance behavior, formulas and required values against the content standard.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Family ID | Parameter Name | Parameter Class | GUID / Built-in ID | Data Type | Group | Type / Instance | Required? | Reporting? | Formula / Association | Values Tested | Result | Issue / Evidence | Owner | Due Date | Notes
FAM-001 | ZX_Clearance_Width | Shared | 00000000-0000-0000-0000-000000000001 | Length | Dimensions | Type | Yes | No |  | 600; 900; 1200 mm | Pass |  | A. Tester | 2026-08-23 | Fictional GUID
FAM-001 | ZX_Clearance_Height | Shared | 00000000-0000-0000-0000-000000000002 | Length | Dimensions | Type | Yes | No |  | 2100; 2400 mm | Pass |  | A. Tester | 2026-08-23 | Fictional GUID
FAM-001 | ZX_Show_3D | Family |  | Yes/No | Graphics | Instance | Yes | No |  | On; Off | Fail | Visibility not applied in coarse view | A. Tester | 2026-08-24 | Fictional
FAM-002 | ZX_Opening_Width | Shared | 00000000-0000-0000-0000-000000000003 | Length | Dimensions | Type | Yes | No |  | 150; 300; 900 mm | Pass |  | A. Tester | 2026-08-23 | Fictional GUID
FAM-002 | ZX_Opening_Height | Shared | 00000000-0000-0000-0000-000000000004 | Length | Dimensions | Type | Yes | No |  | 150; 450; 1200 mm | Pass |  | A. Tester | 2026-08-23 | Fictional GUID
FAM-003 | Manufacturer | Built-in | Built-in | Text | Identity Data | Type | No | No |  | Blank; sample | Pass with note | Not required for planning envelope | B. Reviewer | 2026-08-25 | Fictional
FAM-004 | Arrow_Length | Family |  | Length | Dimensions | Type | Yes | No |  | 3; 6; 12 mm | Pass |  | B. Reviewer | 2026-08-22 | Fictional
FAM-005 | Type Mark | Built-in | Built-in | Text | Identity Data | Instance | Yes | No |  | A; blank | Not tested | Source/license hold |  |  | Fictional

## Type Flex Matrix
Type and geometry flex matrix
Test minimum, typical, maximum and incompatible combinations. Record actual Revit evidence for every release candidate.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Family ID | Type Name / Test Case | Width mm | Depth mm | Height mm | Primary Material | Visibility State | Host / Work Plane | Geometry Flex | Formula Flex | Visibility Flex | Host / Flip | Connector Check | Warnings | Result | Reviewer | Review Date | Evidence URL | Notes
FAM-001 | Minimum | 300 | 300 | 600 | Transparent | 3D on | Level | Pass | Pass | Pass | N/A | N/A | 0 | Pass | A. Tester | 2026-08-22 | https://cde.example/FLEX-001 | Fictional
FAM-001 | Typical | 900 | 900 | 2100 | Transparent | 3D on | Level | Pass | Pass | Fail | N/A | N/A | 1 | Fail | A. Tester | 2026-08-22 | https://cde.example/FLEX-002 | Coarse visibility
FAM-001 | Maximum | 3000 | 3000 | 5000 | Transparent | 3D off | Level | Pass | Pass | Pass | N/A | N/A | 0 | Pass | A. Tester | 2026-08-22 | https://cde.example/FLEX-003 | Fictional
FAM-002 | Minimum | 100 | 100 | 100 | Default | Solid | Face | Pass | Pass | Pass | Pass | N/A | 0 | Pass | A. Tester | 2026-08-22 | https://cde.example/FLEX-004 | Fictional
FAM-002 | Typical | 600 | 300 | 900 | Default | Solid | Face | Pass | Pass | Pass | Pass | N/A | 0 | Pass | A. Tester | 2026-08-22 | https://cde.example/FLEX-005 | Fictional
FAM-002 | Maximum | 2400 | 1200 | 3000 | Default | Solid | Face | Pass | Pass | Pass | Pass | N/A | 0 | Pass | A. Tester | 2026-08-22 | https://cde.example/FLEX-006 | Fictional
FAM-004 | Long arrow | 12 | 0 | 0 | Black | 2D | View | Pass | Pass | Pass | N/A | N/A | 0 | Pass | B. Reviewer | 2026-08-22 | https://cde.example/FLEX-007 | Fictional
FAM-005 | Unverified | 0 | 0 | 0 | Unknown | Unknown | Unknown | Not tested | Not tested | Not tested | Not tested | Not tested | 0 | Not tested |  |  |  | License hold

## Performance
Family performance & complexity review
Record measurable behavior in a controlled test project. Thresholds are project-defined, not universal.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Family ID | Test Revit Build | Test Project ID | File Size KB | Type Count | Nested Count | Imported CAD? | Mesh / High-poly? | Void Count | Array Count | Warnings | Load Time sec | 100-instance Regen sec | Threshold Source | Result | Action | Owner | Due Date | Evidence URL | Notes
FAM-001 | 2022.1.5 | TEST-RVT-001 | 420 | 4 | 0 | No | No | 1 | 0 | 1 | 1.2 | 2.8 | Internal pilot threshold | Pass with note | Resolve warning before release | A. Tester | 2026-08-24 | https://cde.example/PERF-001 | Fictional
FAM-002 | 2022.1.5 | TEST-RVT-001 | 510 | 6 | 0 | No | No | 1 | 0 | 0 | 1.4 | 3.2 | Internal pilot threshold | Pass |  | A. Tester | 2026-08-23 | https://cde.example/PERF-002 | Fictional
FAM-003 | 2022.1.5 | TEST-RVT-001 | 680 | 3 | 0 | No | No | 0 | 0 | 0 | 1.8 | 4.1 | Internal pilot threshold | Pass |  | B. Reviewer | 2026-08-25 | https://cde.example/PERF-003 | Fictional
FAM-004 | 2022.1.5 | TEST-RVT-001 | 96 | 2 | 0 | No | No | 0 | 0 | 0 | 0.5 | 0.9 | Internal pilot threshold | Pass |  | B. Reviewer | 2026-08-22 | https://cde.example/PERF-004 | Fictional
FAM-005 | 2022.1.5 | TEST-RVT-001 | 2450 | 18 | 4 | Unknown | Unknown | 12 | 3 | 14 | 6.8 | 18.2 | No approved threshold | Fail | Quarantine pending source and rebuild review |  |  |  | Fictional

## Release Checklist
Family release checklist
Release only after the supported Revit version, evidence and approval route are recorded.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Family ID | Naming | Category / Host | Origin / References | Constraints / Origin | Type Matrix | Parameters / GUIDs | Materials / Subcategories | Visibility / Detail | Connectors | Performance | Documentation | Thumbnail | Version / Build | License / Source | Final Review | Release Status | Approved By | Approval Date | Release Location | Notes | Completion %
FAM-001 | Pass | Pass | Pass | Pass | Fail | Pass | Pass | Fail | N/A | Pass with note | Pass | Pass | Pass | Pass | Fail | Hold |  |  |  | Resolve visibility and retest
FAM-002 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Released | B. Reviewer | 2026-08-22 | https://library.example/FAM-002 | Fictional release only
FAM-003 | Pass | Pass | Pass | Pass | In review | Pass with note | Pass | Pass | N/A | Pass | In review | Pass | Pass | Pass | In review | Conditional release |  |  |  | Fictional
FAM-004 | Pass | Pass | Pass | Pass | Pass | Pass | Pass | Pass | N/A | Pass | Pass | Pass | Pass | Pass | Pass | Released | B. Reviewer | 2026-08-22 | https://library.example/FAM-004 | Fictional release only
FAM-005 | Not tested | Not tested | Fail | Not tested | Not tested | Not tested | Not tested | Not tested | N/A | Fail | Not tested | Not tested | Pass | Fail | Fail | Rejected |  |  |  | Do not redistribute

## Dashboard
Family QA dashboard
Formula-driven release view. Counts are blank only when there are no registered families.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Metric | Current
Registered families
Released families
Families on hold
Failed parameter tests
Failed flex tests
Failed performance tests
High / critical risk

## Data Dictionary
Data dictionary
Definitions and control intent for the fields most likely to be misused.
FICTIONAL TRAINING EXAMPLE — no RFA files are included or implied by these rows
Sheet | Field | Definition | Input / Formula | Rule
Family Inventory | Family ID | Stable internal identifier linking every test and release record. | Input | Required
Family Inventory | License Checked? | Confirms a human reviewed source and intended-use terms; not automatic permission. | Input | Required before release
Parameter Audit | GUID / Built-in ID | Stable identity for shared or built-in parameters. Fictional examples are not valid standards. | Input | Required where applicable
Type Flex Matrix | Test Case | Boundary or realistic combination tested inside Revit. | Input | Minimum, typical and maximum recommended
Performance | Threshold Source | Named project or library criterion used to judge the result. | Input | Never assume a universal file-size limit
Release Checklist | Final Review | Independent evidence review, distinct from author self-check. | Input | Required before Released
Release Checklist | Completion % | Pass count divided by applicable checks; N/A excluded. | Formula | Planning aid, not approval