ZX COLLABS RESOURCE

BIM Execution Plan

A project-ready framework for information management, BIM production, coordination, review and handover.

Pre-filled fictional example A practical, editable starting point. Adapt it to the appointment, project information requirements, local standards, contracts and delivery method.

Prepared by ZX Collabs

BIM delivery, coordination, documentation and digital workflows

Version 1.0  |  22 August 2026

# How to use this template

This BIM Execution Plan (BEP) is a working management document. Complete it collaboratively, assign named owners, reference controlled project documents instead of duplicating them, and revise it when the appointment, scope, programme or delivery team changes.

FICTIONAL EXAMPLE Northgate Community Health Centre, its organizations, people, dates and identifiers are invented solely to demonstrate how a completed plan can read. Replace every sample entry before project use.

## Completion sequence

Confirm the appointment, project/asset information requirements, exchange milestones and contractual precedence.

Hold a planning workshop with the project manager, information manager, discipline leads and relevant asset representatives.

Complete the responsibility, delivery, review and approval fields with named owners—not only company names.

Test the proposed CDE, software, exchange and quality workflows during mobilization.

Record approval, distribute the controlled edition and review it at agreed trigger points.

## Important boundaries

This template is guidance, not the ISO 19650 standard, legal advice or a substitute for project appointments.

Terminology, status codes, suitability codes, naming conventions and information requirements must follow the project's adopted standard and national annex or guidance.

Specify information by purpose, acceptance criteria and required level of information need; do not rely on an unexplained LOD number.

Check the current published standard and contract requirements. ISO 19650 Parts 1–3 are in revision as of this edition date.

## Document control

| Control | Entry |
| --- | --- |
| Document ID | NGCHC-XX-ZZ-PL-ZX-0001 |
| Revision | P02 |
| Status / suitability | For information / project-defined code S2 |
| Owner | Lead Appointed Party Information Manager |
| Review cycle | At appointment, mobilization, each stage gate and material change |
| Controlled location | Project CDE / Published / Management Plans |

# 1. Project and appointment context

| Field | Project entry |
| --- | --- |
| Project name | Northgate Community Health Centre |
| Project / asset ID | NGCHC-2026 |
| Location | Bristol, United Kingdom |
| Project type | New-build outpatient healthcare facility |
| Appointing party | Northgate Health Estates Ltd (fictional) |
| Lead appointed party | Fieldwork Design & Build Ltd (fictional) |
| Information manager | Amina Shah, Project Information Manager (fictional) |
| Appointment / stage | Design-and-build / coordinated design to construction |
| Planned completion | 30 September 2027 |
| Governing requirements | Employer's information requirements rev P03; project information standard rev P02; appointments |

## 1.1 BIM and information objectives

| ID | Objective | Evidence / measure | Owner |
| --- | --- | --- | --- |
| 01 | Coordinate architecture, structure and building services before construction | Reduced unresolved spatial conflicts at each stage gate | Design manager |
| 02 | Produce reliable construction documentation and model-based quantities | Accepted drawing/model packages and traceable quantity assumptions | Lead appointed party |
| 03 | Deliver maintainable asset information for priority equipment | Validated asset dataset linked to approved records | Asset information lead |

## 1.2 Authorized BIM uses

| BIM use | Responsible party | Deliverable | Purpose / boundary |
| --- | --- | --- | --- |
| Design authoring | All disciplines | Native models and issued sheets | Design development and documentation |
| Federation and clash coordination | BIM coordination team | Federated model, issue records, reports | Weekly coordination cycles |
| 4D planning | Main contractor | Selected model elements linked to construction activities | Sequence validation; not contractual programme replacement |
| Quantity support | Commercial team | Model-derived quantities with exclusions | Benchmark and package review; not automatic valuation |
| Asset handover | Asset information team | Validated priority asset data and record models | Operations readiness |

# 2. Parties, teams and information responsibilities

| Project role | Organization | Information responsibility | Accountable lead |
| --- | --- | --- | --- |
| Appointing party | Northgate Health Estates Ltd | Defines information requirements; accepts/rejects exchanges | Estates Director |
| Lead appointed party | Fieldwork Design & Build Ltd | Coordinates delivery team and master delivery planning | Project Director |
| Architect | Common Ground Studio | Architectural model, room data and drawing production | Architectural BIM Lead |
| Structural engineer | Span Structures | Structural analysis/design model and exchanges | Structural BIM Lead |
| MEP engineer | Vector Building Services | MEP design models, systems data and coordination | MEP BIM Lead |
| Specialist contractors | To be appointed | Fabrication/detail models and product information per package | Package BIM Leads |

## 2.1 Responsibility matrix

| Activity | Appointing party | Lead appointed party | Task teams | Asset team |
| --- | --- | --- | --- | --- |
| Maintain BEP | A | R | C | C |
| Approve information requirements | A/R | C | I | C |
| Maintain MIDP | I | A/R | C | C |
| Author discipline TIDPs | I | A | R | C |
| Federate and run coordination | I | A/R | C | C |
| Approve information exchange | A/R | C | C | C |
| Validate asset data | A | R | C | C |

RACI CHECK One accountable owner per activity is usually clearest. Record delegated information-management tasks without obscuring the appointing party's or appointee's contractual responsibility.

# 3. Information requirements and delivery planning

| ID | Purpose | Information need | Evidence | When |
| --- | --- | --- | --- | --- |
| PIR-01 | Clinical room approval | Room geometry, room names/numbers, equipment zones | Design reviews | Stage 3, Stage 4 |
| PIR-02 | Buildability and coordination | Interfaces, access/clearance zones, penetrations, support assumptions | Clash/issue review | Fortnightly; stage gates |
| PIR-03 | Cost planning | Classified measurable objects; agreed exclusions and measurement rules | Cost reports | Monthly |
| AIR-01 | Maintain priority assets | Stable asset ID, type, location, manufacturer, model, warranty and O&M link | Asset register | Pre-handover and final |

## 3.1 Level of information need

| Element / system | Purpose | Geometry | Data | Documents |
| --- | --- | --- | --- | --- |
| Air-handling units | Plant-room coordination and handover | Overall geometry, connections, access/maintenance zones | System, duty, airflow, electrical load, asset fields | Approved product data and O&M record |
| Internal doors | Room coordination and schedules | Opening, leaf, frame, swing and key interfaces | Type, fire/acoustic rating, hardware set reference | Door schedule and approved submittal |
| Cable trays | MEP coordination | Route, overall size, elevation and critical supports | System/service classification | Coordinated model and installation drawings |

## 3.2 Information delivery plan

| Information container | Deliverable | Team | Milestone | Date | Format | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| NGCHC-AR-ZZ-M3-A-0001 | Architectural model | Architect | Stage 3 coordination | 18 Dec 2026 | Native + IFC + PDF sheets | Architectural BIM Lead |
| NGCHC-ST-ZZ-M3-S-0001 | Structural model | Structural engineer | Stage 3 coordination | 18 Dec 2026 | Native + IFC + PDF | Structural BIM Lead |
| NGCHC-ME-ZZ-M3-M-0001 | Mechanical model | MEP engineer | Stage 3 coordination | 18 Dec 2026 | Native + IFC + PDF | MEP BIM Lead |
| NGCHC-ZZ-ZZ-RP-ZX-0008 | Coordination report | Lead appointed party | Stage 3 gate | 08 Jan 2027 | PDF + issue export | Information manager |

# 4. CDE, information containers and exchange

| Field | Project entry |
| --- | --- |
| CDE platform | Autodesk Construction Cloud (project-controlled tenant) |
| Authoritative location | Project CDE only; email is notification, not record |
| Workflow states | Work in progress → Shared → Published/Documentation → Archived |
| Access control | Role-based least privilege; quarterly and joiner/mover/leaver review |
| Revision/version control | Platform versioning plus project revision rules |
| Backup/retention | Per appointing-party IT policy; final archive retained for agreed period |
| Security classification | Project internal unless specifically classified; no personal/clinical data in models |

## 4.1 Information container identification

| Field | Value / code | Rule |
| --- | --- | --- |
| Project | NGCHC | Project identifier |
| Originator | AR | Authoring organization |
| Volume/system | ZZ | Project-defined spatial/system breakdown |
| Level/location | M3 | Project-defined location |
| Type | M3 | Information container type |
| Role | A | Discipline / role |
| Number | 0001 | Sequential identifier |

PROJECT-SPECIFIC RULE The sequence above is illustrative, not a universal ISO filename. Adopt the project's information standard and national guidance, then test uniqueness and machine readability.

## 4.2 Exchange and interoperability

| Use | Application | Exchange | Control |
| --- | --- | --- | --- |
| Authoring models | Revit 2026 | Native RVT | Weekly WIP backup; shared only after task-team QA |
| Open exchange | IFC 4.3 where supported; otherwise project-approved IFC version | IFC | Validate scope, georeferencing, classes and required properties |
| Coordination | Navisworks Manage 2026 | NWC/NWD + issue export | Federation origin and search sets controlled by coordinator |
| Documents | PDF/A where required | PDF | Sheet/revision metadata and visual check |
| Issues | CDE issues + BCF where supported | Platform record / BCF | Stable issue ID, owner, due date, status and evidence |

# 5. Model production and coordination

## 5.1 Spatial, coordinate and federation strategy

| Field | Project entry |
| --- | --- |
| Survey control | Topographic survey NGCHC-SUR-001 rev P02 |
| Coordinate reference | OSGB36 / British National Grid; project elevation datum documented in survey |
| Project base point | Defined in survey control note; no unapproved relocation |
| Units | Millimetres for authoring; metres for geospatial exchange where required |
| North | True north from survey; project north documented on GA plans |
| Federation breakdown | Architecture, structure, mechanical, electrical, public health and specialist packages |
| Large coordinates test | Coordinate test file accepted during mobilization |

## 5.2 Coordination cycle

Task teams publish quality-checked shared models by Wednesday 12:00.

Coordinator federates accepted models, runs rule-based checks and records issues by Thursday 15:00.

Discipline leads triage issues in Friday coordination meeting; each issue receives one owner and due date.

Authors resolve or respond in native models; screenshots alone do not close an issue.

Coordinator verifies evidence and closes or reopens the issue in the next cycle.

## 5.3 Clash and issue rules

| Rule | Definition | Tolerance | Priority / treatment |
| --- | --- | --- | --- |
| Hard clash | Physical intersection between coordination-authorized elements | 0 mm unless rule states tolerance | Critical / major / minor by impact |
| Clearance | Intrusion into access, maintenance, safety or code zone | Rule-specific zone | Major where operation/code affected |
| Workflow | Sequencing or constructability conflict | No geometry tolerance | Assigned through coordination review |
| Duplicate / false positive | Duplicate objects, placeholders, intended penetrations or invalid search set | Document reason | Exclude only with coordinator approval |

# 6. Quality assurance and acceptance

| Check | Acceptance criterion | When | Owner | Evidence |
| --- | --- | --- | --- | --- |
| File and metadata | Identifier, revision, status, originator and exchange fields complete | Every share | Task-team BIM lead | CDE metadata/checklist |
| Model health | No critical warnings; links, groups, views and file size within agreed thresholds | Weekly / before share | Author + BIM lead | Model health record |
| Coordinates | Approved control retained and discipline alignment test passes | Mobilization + each exchange | Coordinator | Federation test |
| Content scope | Required elements and data present; out-of-scope content removed or identified | Each exchange | Task-team lead | Delivery checklist |
| Open exchange | IFC schema, georeferencing, class/property mapping and visible scope validated | Each IFC exchange | Information manager | IFC validation report |
| Documents | Sheets readable; references, revisions and issue purpose consistent | Each issue | Discipline lead | PDF visual review |
| Security | No unauthorized, sensitive or personal information included | Each share/publish | Information owner | Security check |

## 6.1 Non-conformance and change

Rejected information is returned through the CDE with a reason, owner and required action. Changes affecting requirements, delivery dates, coordinates, model breakdown, software, exchange formats or responsibilities require BEP impact review and controlled revision.

## 6.2 Mobilization tests

| Test | Acceptance | Result | Owner |
| --- | --- | --- | --- |
| CDE access and workflow | All organizations can create, review, share and retrieve test containers | Pass | Information manager |
| Coordinates/federation | Test models align in authoring, federation and IFC viewers | Pass | BIM coordinator |
| Naming/metadata | Test containers validate against project rules | Pass | Document controller |
| Issue workflow | Issue creation, assignment, evidence and closure tested | Pass | BIM coordinator |
| Asset-data exchange | Sample equipment records import to target asset system | Scheduled | Asset information lead |

# 7. Meetings, reporting and capability

| Forum / report | Frequency | Participants | Record / output | Owner |
| --- | --- | --- | --- | --- |
| BIM mobilization | Once before production | All BIM leads | Test outcomes, confirmed workflows | Information manager |
| Coordination meeting | Weekly | Coordinator + discipline leads | Prioritized issue decisions | BIM coordinator |
| Information delivery review | Fortnightly | Project and information managers | MIDP status, risks and overdue decisions | Information manager |
| Stage exchange review | At each exchange | Appointing party + delivery leads | Acceptance/rejection record | Appointing party |
| Handover readiness | Monthly from 6 months before completion | Delivery + asset teams | Asset data/document readiness | Asset information lead |

## 7.1 Capability, capacity and training

| Role / team | Capability | Action / evidence | Due |
| --- | --- | --- | --- |
| Task-team BIM leads | Project standard, CDE workflow, coordination and exchange requirements | Mobilization workshop + test deliverable | Before first shared exchange |
| Model authors | Approved templates, coordinates, content rules and model health | Discipline induction + checklist | Before authoring |
| Reviewers / approvers | Acceptance criteria and CDE review workflow | Role briefing | Before first review |
| Asset team | Asset data fields, validation and target-system import | Sample data test | Before final data population |

# 8. Handover, archive and acceptance

| Deliverable | Content | Format | Acceptance | Owner |
| --- | --- | --- | --- | --- |
| Record models | Approved record geometry and project-defined data | Native + agreed open format | Federation and sample check | Design manager |
| Asset information | Priority assets with stable IDs and required fields | Approved data schema | Automated checks + target-system import | Asset information lead |
| O&M and commissioning | Approved manuals, certificates, test results and links | PDF / native where required | Document register reconciliation | Commissioning manager |
| Issue closure | No open critical issues; accepted residual items logged | CDE issue export | Issue audit | Project manager |
| Archive | Published and superseded controlled record per retention policy | CDE archive package | Retrieval test | Information manager |

## 8.1 Acceptance and sign-off

| Action | Name / role | Date | Status |
| --- | --- | --- | --- |
| Prepared by | Amina Shah — Project Information Manager | 22 August 2026 | Approved for sample use |
| Reviewed by | Daniel Okoro — Project Director | 22 August 2026 | Approved for sample use |
| Approved by | Priya Menon — Estates Director | 22 August 2026 | Approved for sample use |

## 8.2 Revision history

| Rev | Date | Change | Author | Approver |
| --- | --- | --- | --- | --- |
| P01 | 15 Aug 2026 | Initial mobilization draft | A. Shah | D. Okoro |
| P02 | 22 Aug 2026 | Updated exchange plan and asset-data test | A. Shah | P. Menon |

# Sources and further guidance

ISO 19650-1:2018 — concepts and principles (current published edition; revision in progress at edition date): https://www.iso.org/standard/68078.html

ISO 19650-2:2018 — delivery phase of assets: https://www.iso.org/standard/68080.html

ISO 19650-3:2020 — operational phase of assets: https://www.iso.org/standard/75109.html

UK BIM Framework — implementation guidance and resources: https://ukbimframework.org/resources/

ISO 7817-1:2024 — level of information need, concepts and principles: https://www.iso.org/standard/82914.html

Source links are provided for verification and further reading. ZX Collabs has not reproduced the text of the standards. Confirm applicable editions, national annexes, contracts and client requirements before use.