ZX COLLABS RESOURCE

Project Execution Plan

A practical governance framework for scope, programme, commercial control, communication, quality, risk, information and handover.

Pre-filled fictional example A practical, editable starting point. Adapt it to the appointment, project information requirements, local standards, contracts and delivery method.

Prepared by ZX Collabs

BIM delivery, coordination, documentation and digital workflows

Version 1.0  |  22 August 2026

# How to use this template

This Project Execution Plan (PEP) is a working management document. Complete it collaboratively, assign named owners, reference controlled project documents instead of duplicating them, and revise it when the appointment, scope, programme or delivery team changes.

FICTIONAL EXAMPLE Northgate Community Health Centre, its organizations, people, dates and identifiers are invented solely to demonstrate how a completed plan can read. Replace every sample entry before project use.

## Completion sequence

Confirm the appointment, project/asset information requirements, exchange milestones and contractual precedence.

Hold a planning workshop with the project manager, information manager, discipline leads and relevant asset representatives.

Complete the responsibility, delivery, review and approval fields with named owners—not only company names.

Test the proposed CDE, software, exchange and quality workflows during mobilization.

Record approval, distribute the controlled edition and review it at agreed trigger points.

## Important boundaries

This template is guidance, not the ISO 19650 standard, legal advice or a substitute for project appointments.

Terminology, status codes, suitability codes, naming conventions and information requirements must follow the project's adopted standard and national annex or guidance.

Specify information by purpose, acceptance criteria and required level of information need; do not rely on an unexplained LOD number.

Check the current published standard and contract requirements. ISO 19650 Parts 1–3 are in revision as of this edition date.

## Document control

| Control | Entry |
| --- | --- |
| Document ID | NGCHC-XX-ZZ-PL-ZX-0001 |
| Revision | P02 |
| Status / suitability | For information / project-defined code S2 |
| Owner | Lead Appointed Party Information Manager |
| Review cycle | At appointment, mobilization, each stage gate and material change |
| Controlled location | Project CDE / Published / Management Plans |

# 1. Project definition

| Field | Project entry |
| --- | --- |
| Project name | Northgate Community Health Centre |
| Project ID | NGCHC-2026 |
| Client / sponsor | Northgate Health Estates Ltd (fictional) |
| Project director | Daniel Okoro (fictional) |
| Location | Bristol, United Kingdom |
| Delivery model | Two-stage design and build |
| Baseline period | 01 September 2026 to 30 September 2027 |
| Approved budget | GBP 28.0 million (sample only) |
| Plan owner | Project Director |
| Controlled location | Project CDE / Published / Management Plans |

## 1.1 Purpose and success criteria

| Outcome | Success criterion | Measure | Owner |
| --- | --- | --- | --- |
| Clinical capacity | Facility supports the approved room schedule and patient-flow brief | Approved design and commissioning evidence | Sponsor |
| Time | Operational handover by 30 September 2027 | Accepted baseline and milestone reports | Project director |
| Cost | Forecast remains within approved budget and authorized contingency | Monthly cost report | Commercial lead |
| Quality | Zero unresolved critical defects at operational handover | Inspection and defect records | Quality manager |
| Safety | Work delivered under approved HSE plan with learning and corrective action | HSE reporting | HSE manager |
| Information | Accepted project and asset information delivered at each stage gate | CDE acceptance records | Information manager |

## 1.2 Assumptions, constraints and exclusions

| Type | Statement | Potential impact | Owner |
| --- | --- | --- | --- |
| Assumption | Planning approval received before detailed design freeze | Planning delay affects programme | Project director |
| Constraint | Live hospital access route remains operational | Logistics and safety sequencing | Construction manager |
| Constraint | Long-lead electrical equipment procurement | Early design freeze and vendor engagement | Procurement lead |
| Exclusion | Medical equipment procurement by client unless listed in contract | Interface schedule required | Client project manager |

# 2. Governance and organization

| Role | Named lead | Authority / accountability | Governance forum |
| --- | --- | --- | --- |
| Project sponsor | Priya Menon | Approves business-case, budget and major scope decisions | Monthly board; stage gates |
| Project director | Daniel Okoro | Accountable for integrated delivery and escalation | Weekly leadership review |
| Design manager | Lena Brooks | Coordinates design scope, interfaces and approvals | Design review |
| Commercial lead | Marco Silva | Cost, procurement, change valuation and forecast | Monthly commercial review |
| Construction manager | Harriet Cole | Site delivery, logistics, sequencing and trade coordination | Daily/weekly production |
| Information manager | Amina Shah | Information requirements, CDE, delivery planning and acceptance | Information delivery review |
| HSE manager | Noah Williams | HSE planning, assurance and incident learning | Weekly HSE review |
| Quality manager | Mei Chen | Quality plan, inspections, non-conformance and closeout | Quality review |

## 2.1 Decision and escalation matrix

| Decision | Authority | Escalation / recommendation | Time |
| --- | --- | --- | --- |
| Technical design within approved scope | Design manager | Project director | 3 working days |
| Change up to GBP 25,000 within contingency | Project director | Sponsor notified | 5 working days |
| Change above GBP 25,000 or scope/time impact | Sponsor / board | Project director recommends | Next board or emergency review |
| Safety stop-work | Any person may stop; HSE manager controls restart | Project director | Immediate |
| Information exchange acceptance | Appointing-party representative | Information manager assesses | Per exchange schedule |

# 3. Scope and delivery strategy

| Workstream | Scope | Deliverable | Owner |
| --- | --- | --- | --- |
| Design | Architecture, structure, MEP, landscape and specialist coordination | Accepted design packages and approvals | Design manager |
| Enabling works | Site establishment, surveys, utilities diversions and temporary works | Area ready for main works | Construction manager |
| Main works | Substructure, frame, envelope, fit-out, systems and external works | Completed and tested facility | Construction manager |
| Commissioning | Integrated testing, training, seasonal plan and statutory evidence | Operational readiness | Commissioning manager |
| Information handover | Record information, asset data, O&M, approvals and archive | Accepted information package | Information manager |

## 3.1 Interface register

| ID | Interface | Dependency / decision | Owner | Need date |
| --- | --- | --- | --- | --- |
| IF-01 | Client medical equipment / building services | Equipment loads and connection points | Design manager | Stage 3 freeze |
| IF-02 | Existing utilities / new incoming services | Survey confidence and authority approvals | Utilities lead | Before enabling works |
| IF-03 | Envelope / MEP penetrations | Waterproofing, fire and support details | Design manager | Before fabrication |
| IF-04 | BMS / asset information platform | Point naming, IDs and data mapping | Digital lead | Before commissioning |

## 3.2 Delivery principles

Freeze decisions only when inputs, acceptance criteria and downstream impact are visible.

Plan work by deliverable and interface, not only by discipline.

Keep one controlled source for programme, cost, risk, change and information records.

Use progressive assurance; do not defer all validation to practical completion.

# 4. Programme, planning and controls

| ID | Milestone | Baseline | Acceptance | Owner |
| --- | --- | --- | --- | --- |
| M01 | Mobilization complete | 30 Sep 2026 | CDE, roles, baseline and controls operational | Project director |
| M02 | Coordinated design freeze | 31 Mar 2027 | Approved coordinated design and outstanding-decision register | Design manager |
| M03 | Envelope watertight | 30 Jun 2027 | Inspection records and weather-tight certificate | Construction manager |
| M04 | Systems ready for integrated testing | 15 Aug 2027 | Pre-commissioning complete | Commissioning manager |
| M05 | Operational handover | 30 Sep 2027 | Accepted facility, information, training and residual-item plan | Project director |

## 4.1 Planning rules

| Control | Rule | Owner |
| --- | --- | --- |
| Baseline | Integrated level 3 programme approved at mobilization | Project director |
| Look-ahead | Six-week look-ahead updated weekly with constraints and owners | Construction manager |
| Progress | Physical progress supported by agreed evidence; no unsupported percentage claims | Planner |
| Critical path | Reviewed weekly; material movement escalated within two working days | Planner |
| Recovery | Owner, action, dates and resource/cost implications recorded | Workstream lead |

## 4.2 Reporting dashboard

| Area | Measures | Cadence | Owner |
| --- | --- | --- | --- |
| Schedule | Milestone variance; critical path; look-ahead constraints | Weekly | Planner |
| Cost | Committed, actual, forecast, contingency and change exposure | Monthly | Commercial lead |
| Risk | Top risks, trend, overdue treatments and quantitative exposure | Fortnightly | Project director |
| Safety | Leading/lagging indicators, actions and learning | Weekly | HSE manager |
| Quality | Inspection completion, NCR ageing, defects and closeout trend | Weekly | Quality manager |
| Information | MIDP status, exchanges, rejection reasons and overdue decisions | Fortnightly | Information manager |

# 5. Commercial, procurement and change control

| Package | Procurement route | Dependency | Need date | Status |
| --- | --- | --- | --- | --- |
| Structural steel | Design-assist subcontract | Design capacity and connection interfaces | 15 Oct 2026 | Awarded |
| Envelope | Two-stage specialist package | Performance specification and sample approval | 01 Dec 2026 | Tender |
| Air-handling units | Early equipment order | Approved duties, dimensions and controls | 15 Nov 2026 | Design freeze |
| BMS integration | Specialist package | Point schedule, cybersecurity and platform interfaces | 31 Jan 2027 | Prequalification |

## 5.1 Change workflow

Originator raises a change record with reason, affected requirements and required decision date.

Design, programme, cost, safety, quality, information and operational impacts are assessed by named owners.

Authorized decision-maker approves, rejects or requests options within the delegated authority matrix.

Approved change updates the controlled baseline, documents, models, programme, cost forecast and risk record.

Implementation and effectiveness are verified before closure.

## 5.2 Change register fields

| ID | Change | Reason | Impact | Authority | Status |
| --- | --- | --- | --- | --- | --- |
| CH-014 | Increase UPS autonomy for clinical systems | Client operational resilience review | GBP 42,000 / 8 days if late | Sponsor | Assessment |

# 6. Risk, opportunity and issue management

| ID | Description | P | I | Score | Treatment | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Late utility diversion approval | 4 | 4 | 16 High | Early authority workshop; protect alternate sequence | Utilities lead | Open |
| R-02 | MEP plant procurement exceeds lead time | 3 | 5 | 15 High | Early technical freeze and supplier capacity check | Procurement lead | Open |
| R-03 | Incomplete asset data at handover | 3 | 4 | 12 High | Sample import and progressive data validation | Information manager | Open |
| O-01 | Standardized room modules | 3 | 4 | 12 Opp. | Prototype repeatable coordinated room types | Design manager | Assess |

## 6.1 Rules

Score probability and impact against the approved project matrix; do not compare raw scores from different matrices.

Every treatment has an owner and due date. Review residual risk after the action, not only before it.

Convert an uncertainty that has occurred into an issue with a recovery/decision plan; retain its risk history.

Escalate risks that exceed delegated tolerance or threaten a stage gate, safety, compliance or operational readiness.

## 6.2 Issue and decision log

| ID | Issue / decision | Owner | Action / evidence | Due | Status |
| --- | --- | --- | --- | --- | --- |
| I-007 | MRI vendor load data not confirmed | Design manager | Vendor meeting and provisional design envelope | 28 Aug 2026 | Open |
| D-011 | Select open or closed ceiling in main corridor | Sponsor | Option comparison with infection-control and maintenance impact | 05 Sep 2026 | Pending |

# 7. Quality, HSE and sustainability

## 7.1 Quality control plan

| Subject | Acceptance | Verification | When | Owner |
| --- | --- | --- | --- | --- |
| Design packages | Approved brief, coordination, compliance and information requirements | Design review and independent check | Each issue | Design manager |
| Mock-ups / samples | Approved appearance and performance criteria | Inspection and recorded approval | Before bulk work | Quality manager |
| Installed work | ITP hold/witness points and approved construction information | Inspection, test and photo evidence | Per ITP | Construction manager |
| Commissioning | Approved scripts and acceptance criteria | Witnessed testing and results | System completion | Commissioning manager |
| Handover | Complete, accurate and retrievable records | Register reconciliation and sample retrieval | Monthly closeout | Information manager |

## 7.2 HSE management

| Area | Requirement | Owner |
| --- | --- | --- |
| Governance | Project-specific HSE plan; statutory and client requirements | HSE manager |
| Design risk | Eliminate/reduce hazards; communicate residual risks in controlled records | Design manager |
| Planning | Task risk assessment/method statement and permit controls | Construction manager |
| Learning | Near-miss, observation and incident review; corrective actions verified | HSE manager |
| Stop work | Any person may stop unsafe work without retaliation | Project director |

## 7.3 Sustainability and social value

| Outcome | Target / action | Evidence | Owner |
| --- | --- | --- | --- |
| Operational energy | Meet approved energy target and verify controls | Energy model + commissioning data | Design/commissioning leads |
| Embodied carbon | Record agreed high-impact materials and options | Project carbon report | Design manager |
| Waste | Prevent, segregate and report priority waste streams | Waste records | Construction manager |
| Inclusive access | Validate approved access and wayfinding requirements | Design review + inspection | Design manager |
| Local value | Report agreed training/local supply outcomes without double counting | Social-value report | Project director |

# 8. Communication, documents and information

| Forum | Participants | Cadence | Purpose / output | Owner |
| --- | --- | --- | --- | --- |
| Project board | Sponsor, project director, key client leads | Monthly | Decisions, tolerances, forecast and top risks | Project director |
| Delivery leadership | Workstream leads | Weekly | Milestones, interfaces, constraints and decisions | Project director |
| Design coordination | Design disciplines and specialist packages | Weekly | Coordinated design and issue decisions | Design manager |
| Commercial review | Project/commercial/procurement leads | Monthly | Forecast, change, procurement and contingency | Commercial lead |
| Stakeholder briefing | Users, operations and affected neighbors as applicable | Milestone-based | Decisions, impacts and feedback | Stakeholder lead |

## 8.1 Document and correspondence rules

| Control | Rule | Owner |
| --- | --- | --- |
| Authoritative record | Project CDE; email may notify but does not replace controlled records | Information manager |
| Document identifiers | Project information standard and agreed metadata | Document controller |
| Reviews | Named reviewer, due date, status and consolidated response | Package owner |
| RFIs | Single question/decision per record; location, evidence and required-by date | Design manager |
| Meeting records | Decisions, actions, owners and dates; issued within two working days | Meeting chair |
| Personal/sensitive data | Collect minimally; restrict access; follow project privacy/security rules | Information owner |

## 8.2 BIM and digital delivery reference

The project BIM Execution Plan governs BIM-specific information management, model production, exchange, coordination, quality and handover. This PEP references the controlled BEP and does not duplicate its technical rules.

# 9. Commissioning, handover and closeout

| Item | Acceptance / evidence | Owner | Due / status |
| --- | --- | --- | --- |
| Commissioning plan | Systems, scripts, witnesses, dependencies and acceptance criteria | Commissioning manager | Approved before testing |
| Training | Role-based operator training with attendance and materials | Operations lead | Before operational handover |
| Handover documents | Approved manuals, certificates, warranties, test results and record information | Information manager | Progressively validated |
| Asset data | Priority assets with stable IDs and accepted required fields | Asset information lead | Imported/tested before final |
| Defects / residual work | Prioritized list, owners, dates and operational controls | Quality manager | Accepted at handover |
| Lessons learned | Evidence-based review covering outcomes, controls and reusable learning | Project director | Within 30 days |
| Archive | Controlled project record retained and retrievable per policy | Information manager | Archive test complete |

## 9.1 Plan approval

| Action | Name / role | Date | Status |
| --- | --- | --- | --- |
| Prepared by | Daniel Okoro — Project Director | 22 August 2026 | Approved for sample use |
| Reviewed by | Marco Silva — Commercial Lead | 22 August 2026 | Approved for sample use |
| Approved by | Priya Menon — Project Sponsor | 22 August 2026 | Approved for sample use |

## 9.2 Revision history

| Rev | Date | Change | Author | Approver |
| --- | --- | --- | --- | --- |
| P01 | 15 Aug 2026 | Mobilization draft | D. Okoro | P. Menon |
| P02 | 22 Aug 2026 | Baseline, controls and handover updates | D. Okoro | P. Menon |

# Reference framework

## Before controlled issue

Confirm every accountable role is named and accepts the stated authority.

Reconcile scope, milestones, budget, procurement, risk and information plans against the approved baseline.

Verify that referenced plans and registers use the same identifiers, dates and controlled locations.

Remove unused example content and complete the approval and revision records.

## Useful references

Use the applicable appointment, contract, local law and client governance as the controlling basis.

Where BIM/information management is required, coordinate this PEP with the project BEP and current ISO 19650/national guidance.

ISO 21502:2020 provides general project-management guidance: https://www.iso.org/standard/74947.html

UK BIM Framework implementation guidance: https://ukbimframework.org/resources/

This template is a practical starting point, not legal, contractual, safety or regulatory advice. Adapt it with competent project, commercial, HSE, quality, information and legal professionals.